## Traceability Matrix
Traceability Matrix
Prototype Title: | Purr-loin
Scope: | This game is a third-person stealth / sneaking game. The player must use their skills as a cat-burglar to sneak past guard dogs and gather valuables as they work to complete their mission. The player will have a primary objective (level-based), a secondary objective (to escape), and a bonus objective (to gather additional valuables from the level).
Bitbucket Repository Link: | https://bitbucket.org/johnson-arena-c3-2024/johnson_arena/src/main/
Class | Functionality | Implementation Description | Program | Begin Phase | Complete Phase | Assigned to | Completed? Y/N | Notes
Example: Player Character | Example: Movement | Example: Utilize WASD input keys to control player speed and direction. | Example: Unreal Engine 5 | Example: Pre-alpha | Example: Alpha | Example: Self | Example: Yes | Example: Movement is completed, but inputs need to be added to project settings.
Player Character | Movement | Utilize WASD input keys to control player speed and direction. | Unreal Engine 5.4.0, Git, | Alpha | Alpha | E. Johnson, | Yes | Base movement is implemented (WASD), additional inputs may be needed
Player Character | Pick-up Items | Utilize E input key to interact / pick up objects. | Unreal Engine 5.4.0, Git, | Alpha | Alpha | E. Johnson, | Yes | Input is implemented and items can be interacted with / taken. Appropriate tracking of items and associated player state is updated when an item is taken.
Player Character | Item scoring | Implement the scoring for bonus item pickups | Unreal Engine 5.4.0, Git, | Alpha | Alpha | E. Johnson, | Yes | Base system implemented, GUI implemented and tracks / updates value. Valuables added of 3 varieties. Objective items, 10 points, and 50 points.
Player Character | Hide interaction | Utilize tab input key to hide the player behind an object / terrain. | Unreal Engine 5.4.0, Git, | Alpha | Alpha | E. Johnson, | Yes | Implemented fully, Hold crouch while in the marked spaces to trigger the hiding state for the player
Player Character | Model | Base model selection and implementation for the player character | Unreal Engine 5.4.0, Git, | Beta | Beta | E. Johnson, | No | Not yet implemented/placeholder used, will be in Beta+. Ran out of time for this development cycle.
Player Character | Animations | Implement animations for the player model for the various interactions | Unreal Engine 5.4.0, Git, | Beta | Beta | E. Johnson, | No | Not yet implemented/placeholder used, will be in Beta+. Ran out of time for this development cycle.
Player Character | Movement: Jump | Utilize the space bar to allow the player to jump over obstacles or traps such as laser detector beams | Unreal Engine 5.4.0, Git, | Alpha | Alpha | E. Johnson, | Yes | Jump movement is implemented and working. When the player presses space bar, their character will move vertically.
Player Character | Movement: Crouch | Utilize the C / Control button to allow the player to crouch into smaller spaces. | Unreal Engine 5.4.0, Git, | Alpha | Beta | E. Johnson, | Yes | Implemented and working as intended. No animation is implemented, but the model will get smaller, and the action is executed
Player Character | Trap interaction | The player will press F to interact with a trap, attempting to use their disarming skills (claw) to pick / disable the trap | Unreal Engine 5.4.0, Git, | Alpha | Alpha | E. Johnson, | Yes | This was implemented in the form of a central power switch that the player will need to find the key to turn off. Once it is deactivated all of the lasers will be deactivated, allowing the player to proceed to the next area of the level
Security Guard Dog: NPC | Movement | Implement patrol paths for controlling the range of a guard | Unreal Engine 5.4.0, Git, | Alpha | Alpha | E. Johnson, | Yes | Implemented / Working fully. There are around a dozen guards each with unique patrol paths.
Security Guard Dog: NPC | Vision | Implement visual cues to show the distance that a guard can see the player from (i.e. flashlight beam) | Unreal Engine 5.4.0, Git, | Alpha | Alpha | E. Johnson, | Yes | Basic flashlight beam implemented to show overlap trigger /catch range.
Security Guard Dog: NPC | Interactions | Implement the interaction with a player (Catching a player) | Unreal Engine 5.4.0, Git, | Alpha | Alpha | E. Johnson, | Yes | Catch system for patrol guards is implemented and working as intended. Correctly respects environment collision.
Security Guard Dog: NPC | Model | Implement the model selection for the guard dog NPC | Unreal Engine 5.4.0, Git, | Beta | Beta | E. Johnson, | No | Not yet implemented/placeholder used, will be in Beta+. Ran out of time for this development cycle.
Security Guard Dog: NPC | Animations | Model animations for the guard dog | Unreal Engine 5.4.0, Git, | Beta | Beta | E. Johnson, | No | Not yet implemented/placeholder used, will be in Beta+. Ran out of time for this development cycle.
Security Camera: Game Obstacle / Trap | Object | Implement the object / class for security camera | Unreal Engine 5.4.0, Git, | Alpha | Alpha | E. Johnson, | Yes | Fully implemented and working as intended. It rotates on a timeline, moving its vision cone 45 degrees left, back to 0, then 45 degrees right, and back to 0.
Security Camera: Game Obstacle / Trap | Vision | Implement visual cues to show the distance that a security camera can see the player from (i.e. tracking laser paired with overlap trigger area) | Unreal Engine 5.4.0, Git, | Alpha | Alpha | E. Johnson, | Yes | Implemented and working as intended. Respects collision with environment such as walls.
Security Camera: Game Obstacle / Trap | Animations | Implement animations security camera | Unreal Engine 5.4.0, Git, | Beta | Beta | E. Johnson, | Yes | The camera model may be adjusted at a later date, but the camera correctly moves along the choreographed timeline.
Laser Beam Trip-wire: Game Obstacle / Trap | Object | Implement a laser beam trip fire that features a very tight overlap trigger that will cause alarms to be set off and the player to be found if they do not maneuver around it. | Unreal Engine 5.4.0, Git, | Alpha | Beta | E. Johnson, | Yes | Implemented and working as intended. All beams are tied to a central power switch. Touching a beam will cause the player to be sent back to spawn
Laser Beam Trip-wire: Game Obstacle / Trap | Animations | Implement animations / variations for any laser trip wires that have movement / alternative patterns. | Unreal Engine 5.4.0, Git, | Beta | Beta | E. Johnson, | No | Beams are implemented and working. Did not implement any traps that utilized moving beams. That feature was limited to the security cameras.
Player Character | Level failure (Player character death / damage) | Implement the level failure mechanic that will be called whenever the player character triggers a trap or is caught by one of the other obstacles they may face | Unreal Engine 5.4.0, Git, | Alpha | Alpha | E. Johnson, | Yes | Implemented, tied to player health reaching 0.
User interface: Score Value Widget | Graphical User Interface | Implement GUI valuable score tracker for player U.I. | Unreal Engine 5.4.0, Git, | Alpha | Beta | E. Johnson, | Yes | Implemented and working. Correctly increments score value on items of different values
User interface: Objective widget | Graphical User Interface | Implement GUI main objective tracker for player U.I. | Unreal Engine 5.4.0, Git, | Alpha | Beta | E. Johnson, | Yes | Implemented and working. Correctly records actions that would complete the listed objective
User interface: Objective widget | Graphical User Interface | Implement GUI secondary objective tracker for player U.I. | Unreal Engine 5.4.0, Git, | Alpha | Beta | E. Johnson, | Yes | Implemented and working. Correctly records actions that would complete the listed objective
User interface: Objective widget | Graphical User Interface | Implement GUI third objective tracker for player U.I. | Unreal Engine 5.4.0, Git, | Alpha | Beta | E. Johnson, | Yes | Implemented and working. Correctly records actions that would complete the listed objective
Features that were removed from planning
Game mechanic | Level timer | Implement a timer for the level. The player will fail the level if the timer runs out before they have completed the main objective and reached the exit / escape point | Unreal Engine 5.4.0, Git, | Alpha | Alpha | E. Johnson, | No | Core game feature, not yet implemented. High priority
User interface: Hide Widget | GUI – is player hidden? | Implement player U.I. visibility / status tracker | Unreal Engine 5.4.0, Git, | Alpha | Beta | E. Johnson, | No | Not yet implemented, will be in Beta +

## Test Plan
Test Plan
Bitbucket Repository Link: | https://bitbucket.org/johnson-arena-c3-2024/johnson_arena/src/main/
Test Feature | Description of Test | Pass/Fail | Bugs | Runtime Errors | Updates/Error Resolution
Example: Pickup interaction | Example: Implement print strings to ensure player input is firing and appropriate events are being called. Display class name on interaction via print string to ensure the correct class is interacting. | Example: Fail | Example: Pickup interaction functions, but integer doesn't increment properly. | Example: Accessed None when trying to read Pickup_BP | Example: Verify item interaction is setting the Pickup_BP references variable properly. An issue here may be why the variable cannot be accessed by the editor.
Player Character Tests:
Item / objective pickup interaction | When an object is picked up by the player, bonus objective or primary objective should be updated respectively | PASS | N/A – No bugs with currently implemented features. Can currently successfully bind a “key” item to a specific door / object. | N/A. No runtime error occurs | Additional item implementations / actions will be required. Currently limited to key pickup item, and operating locked doors w/ a key, or unlocked doors.
Player score increment on item pickup | When a player picks up an object that is tied to the bonus objective class, the bonus score should be appropriately incremented to reflect the pickup | PASS | Pickup interaction works correctly, but items tied to the bonus score is not yet implemented | N/A. No runtime error occurs | Implement an incrementing to the score value to occur when an item that is designated as a bonus objective class is picked up. Implement score values along with additional item pickups.
Player objective HUD updates objective statuses | When a player picks up or interacts with an items that should trigger a level objective to complete, the objective text changes from incomplete, to complete. | PASS | Had trouble getting the objective fields to correctly update. | N/A. No runtime error occurs | Simplified the process to just update the complete / incomplete verbiage instead of the entire objective string.
Player hiding won’t be detected | When a player has successfully triggered the hide ability, they should be hidden from any patrolling guard dogs. | PASS | Currently no interaction between the isHidden status, and the guards catching the player. | N/A. No runtime error occurs | Implement a player character input to trigger hide. Implement boolean state variable to check whether the player is currently hidden
Player hiding status triggered and event changes | When a player has successfully triggered the hide ability, state changes tied to hiding should occur | PASS | Single interaction added to change material of arrow above hiding spot. Currently not working. | N/A. No runtime error occurs | Implement actor state change mechanics that are correctly tied to and triggered by the isHidden status becoming true.
Enemy Tests:
Guard dogs patrol along paths defined by assigned waypoints | Guards will continue patrolling along their associate patrol path. | PASS | Only a single guard / patrol path is working as intended. Additional guards / paths cause their guards to walk to the center of the path, and then stop moving. | N/A. No runtime error occurs | Implement a condition to tie specific guard / enemy instances to additional patrol path instances.
Guard dogs catch the player when seen | Guards will correctly catch a player who is close enough and within their overlap box. | PASS | Guards were catching the player through hard collision / walls. | N/A. No runtime error occurs | Collision for the overlap box was correctly re-setup to interact with the player model capsule. A line trace and conditional branch was added to the overlap event to ensure that players are only caught when not hiding or behind cover.
Security camera catches player when they are within the overlap / trigger area for the camera | When a player is detected as having crossed into the trigger area of a security camera’s vision / catch event, the player should be caught, triggering a mission failure. | PASS | Cameras were catching players through walls. | N/A. No runtime error occurs | A similar approach was used to fix this problem, and the cameras now correctly respect the collision of walls / objects.
Laser security beam trap will trigger when a player passes through the trigger range that is associated with the laser’s beam. | When a player crosses too close (passes through or makes contact) to the laser beam, alarms are sounded and the player is caught. | PASS | The catch mechanic is not yet implemented, the laser beam and associated trigger / detection radius must also be implemented first | N/A. No runtime error occurs | This will be fixed by implementing a tight trigger radius within the beam of the laser. The laser beam must be implemented, and the begin trigger range should trigger the catch mechanism once it is also implemented.
Laser tripwires will correctly be disabled when the power switch for security has been turned off. | All laser tripwires can be enabled or disabled via the power switch so long as the player has the matching key | PASS | Had problems getting all lasers and correctly turning them off. | N/A. No runtime error occurs | Corrected by adding a new LaserPowerBP. It contains a reference array of lasers, and 3 functions. Add lasers, which populates the reference array of all lasers, enable lasers, which sets the collision and visibility of all lasers to on, and then disable when sets the visibility/collision of all lasers to off.