## Traceability Matrix
Traceability Matrix
Prototype Title: | Purr-loin
Scope: | This game is a third-person stealth / sneaking game. The player must use their skills as a cat-burglar to sneak past guard dogs and gather valuables as they work to complete their mission. The player will have a primary objective (level-based), a secondary objective (to escape), and a bonus objective (to gather additional valuables from the level).
Bitbucket Repository Link: | https://bitbucket.org/johnson-arena-c3-2024/johnson_arena/src/main/
Class | Functionality | Implementation Description | Program | Begin Phase | Complete Phase | Assigned to | Completed? Y/N | Notes
Example: Player Character | Example: Movement | Example: Utilize WASD input keys to control player speed and direction. | Example: Unreal Engine 5 | Example: Pre-alpha | Example: Alpha | Example: Self | Example: Yes | Example: Movement is completed, but inputs need to be added to project settings.
Player Character | Movement | Utilize WASD input keys to control player speed and direction. | Unreal Engine 5.4.0, Git, | Alpha | Alpha | E. Johnson, | Yes | Base movement is implemented (WASD), additional inputs may be needed
Player Character | Pick-up Items | Utilize E input key to interact / pick up objects. | Unreal Engine 5.4.0, Git, | Alpha | Alpha | E. Johnson, | Yes | Input is implemented and items can be interacted with / taken. No system is currently implemented to handle storage / tracking of picked up items.
Player Character | Item scoring | Implement the scoring for bonus item pickups | Unreal Engine 5.4.0, Git, | Alpha | Alpha | E. Johnson, | Yes | Base system implemented, no GUI / tied functions.
Player Character | Hide interaction | Utilize tab input key to hide the player behind an object / terrain. | Unreal Engine 5.4.0, Git, | Alpha | Alpha | E. Johnson, | Partially | Hide input and object interaction has not yet been implemented.
Player Character | Model | Base model selection and implementation for the player character | Unreal Engine 5.4.0, Git, | Beta | Beta | E. Johnson, | No | Not yet implemented, will be in Beta +
Player Character | Animations | Implement animations for the player model for the various interactions | Unreal Engine 5.4.0, Git, | Beta | Beta | E. Johnson, | No | Not yet implemented, will be in Beta +
Player Character | Movement: Jump | Utilize the space bar to allow the player to jump over obstacles or traps such as laser detector beams | Unreal Engine 5.4.0, Git, | Alpha | Alpha | E. Johnson, | Yes | Jump movement is implemented and working. When the player presses space bar, their character will move vertically.
Player Character | Movement: Crouch | Utilize the C / Control button to allow the player to crouch into smaller spaces. | Unreal Engine 5.4.0, Git, | Alpha | Beta | E. Johnson, | Partially | Implementation may be tied to the hide ability if the player crouches within a specific area. Currently working on implementing. Inputs are added.
Player Character | Trap interaction | The player will press F to interact with a trap, attempting to use their disarming skills (claw) to pick / disable the trap | Unreal Engine 5.4.0, Git, | Alpha | Alpha | E. Johnson, | No | The input key will need to be created, as well as the animation for this ability, and each corresponding trap will need the interaction area/range for this ability to be defined
Security Guard Dog: NPC | Movement | Implement patrol paths for controlling the range of a guard | Unreal Engine 5.4.0, Git, | Alpha | Alpha | E. Johnson, | Yes | Implemented / Working. Need to add functionality to bind specific EnemyAi to selected patrol path.
Security Guard Dog: NPC | Vision | Implement visual cues to show the distance that a guard can see the player from (i.e. flashlight beam) | Unreal Engine 5.4.0, Git, | Alpha | Alpha | E. Johnson, | Yes | Basic flashlight beam implemented to show overlap trigger /catch range.
Security Guard Dog: NPC | Interactions | Implement the interaction with a player (Catching a player) | Unreal Engine 5.4.0, Git, | Alpha | Alpha | E. Johnson, | Yes | System for catching a player / failing the level not yet implemented
Security Guard Dog: NPC | Model | Implement the model selection for the guard dog NPC | Unreal Engine 5.4.0, Git, | Beta | Beta | E. Johnson, | No | Not yet implemented/placeholder used, will be in Beta +
Security Guard Dog: NPC | Animations | Model animations for the guard dog | Unreal Engine 5.4.0, Git, | Beta | Beta | E. Johnson, | No | Not yet implemented/placeholder used, will be in Beta +
Security Camera: Game Obstacle / Trap | Object | Implement the object / class for security camera | Unreal Engine 5.4.0, Git, | Alpha | Alpha | E. Johnson, | Partially | Will be tied to a “turret”, that is already implemented. Needs to have detection beam / overlap tied to player and movement should be based on a timer instead of auto-targetting player when they enter the overlap range.
Security Camera: Game Obstacle / Trap | Vision | Implement visual cues to show the distance that a security camera can see the player from (i.e. tracking laser paired with overlap trigger area) | Unreal Engine 5.4.0, Git, | Alpha | Alpha | E. Johnson, | No | Not yet implemented
Security Camera: Game Obstacle / Trap | Animations | Implement animations security camera | Unreal Engine 5.4.0, Git, | Beta | Beta | E. Johnson, | No | Not yet implemented, will be in Beta +
Laser Beam Trip-wire: Game Obstacle / Trap | Object | Implement a laser beam trip fire that features a very tight overlap trigger that will cause alarms to be set off and the player to be found if they do not maneuver around it. | Unreal Engine 5.4.0, Git, | Alpha | Beta | E. Johnson, | No | Not yet implemented. Should be added along with guard dogs, and security cameras as the primary obstacles players to face.
Laser Beam Trip-wire: Game Obstacle / Trap | Animations | Implement animations / variations for any laser trip wires that have movement / alternative patterns. | Unreal Engine 5.4.0, Git, | Beta | Beta | E. Johnson, | No | Not yet implemented. Should be added along with guard dogs, and security cameras as the primary obstacles for players to face.
Game mechanic | Level timer | Implement a timer for the level. The player will fail the level if the timer runs out before they have completed the main objective and reached the exit / escape point | Unreal Engine 5.4.0, Git, | Alpha | Alpha | E. Johnson, | No | Core game feature, not yet implemented. High priority
Player Character | Level failure (Player character death / damage) | Implement the level failure mechanic that will be called whenever the player character triggers a trap or is caught by one of the other obstacles they may face | Unreal Engine 5.4.0, Git, | Alpha | Alpha | E. Johnson, | Yes | Implemented, tied to player health reaching 0.
User interface: Score Value Widget | Graphical User Interface | Implement GUI valuable score tracker for player U.I. | Unreal Engine 5.4.0, Git, | Alpha | Beta | E. Johnson, | No | Not yet implemented, will be in Beta +
User interface: Objective widget | Graphical User Interface | Implement GUI main objective tracker for player U.I. | Unreal Engine 5.4.0, Git, | Alpha | Beta | E. Johnson, | No | Not yet implemented, will be in Beta +
User interface: Objective widget | Graphical User Interface | Implement GUI secondary objective tracker for player U.I. | Unreal Engine 5.4.0, Git, | Alpha | Beta | E. Johnson, | No | Not yet implemented, will be in Beta +
User interface: Hide Widget | GUI – is player hidden? | Implement player U.I. visibility / status tracker | Unreal Engine 5.4.0, Git, | Alpha | Beta | E. Johnson, | No | Not yet implemented, will be in Beta +

## Test Plan
Test Plan
Bitbucket Repository Link: | https://bitbucket.org/johnson-arena-c3-2024/johnson_arena/src/main/
Test Feature | Description of Test | Pass/Fail | Bugs | Runtime Errors | Updates/Error Resolution
Example: Pickup interaction | Example: Implement print strings to ensure player input is firing and appropriate events are being called. Display class name on interaction via print string to ensure the correct class is interacting. | Example: Fail | Example: Pickup interaction functions, but integer doesn't increment properly. | Example: Accessed None when trying to read Pickup_BP | Example: Verify item interaction is setting the Pickup_BP references variable properly. An issue here may be why the variable cannot be accessed by the editor.
Item / objective pickup interaction | When an object is picked up by the player, bonus objective or primary objective should be updated respectively | Pass | N/A – No bugs with currently implemented features. Can currently successfully bind a “key” item to a specific door / object. | N/A. No runtime error occurs | Additional item implementations / actions will be required. Currently limited to key pickup item, and operating locked doors w/ a key, or unlocked doors.
Player score increment on item pickup | When a player picks up an object that is tied to the bonus objective class, the bonus score should be appropriately incremented to reflect the pickup | Fail | Pickup interaction works correctly, but items tied to the bonus score is not yet implemented | N/A. No runtime error occurs | Implement an incrementing to the score value to occur when an item that is designated as a bonus objective class is picked up. Implement score values along with additional item pickups.
Player hiding won’t be detected | When a player has successfully triggered the hide ability, they should be hidden from any patrolling guard dogs. | Fail | Currently no interaction between the isHidden status, and the guards catching the player. | N/A. No runtime error occurs | Implement a player character input to trigger hide. Implement boolean state variable to check whether the player is currently hidden
Player hiding status triggered and event changes | When a player has successfully triggered the hide ability, state changes tied to hiding should occur | Fail | Single interaction added to change material of arrow above hiding spot. Currently not working. | N/A. No runtime error occurs | Implement actor state change mechanics that are correctly tied to and triggered by the isHidden status becoming true.
Guard dog catches player in line of sight / within overlap trigger area | When a player is detected as having crossed into the trigger area of a guard dog’s catch event, the player should be caught, triggering a mission failure. | Pass | Guard / Enemy correctly patrols path, if player is caught in the guard’s flashlight beam, they are killed / respawned. | N/A. No runtime error occurs | Implement a mission / checkpoint reset mechanic to be triggered on player death. Currently no reset, just a respawn at the single respawn point.
Guard dogs patrol along paths defined by assigned waypoints | Guards will continue patrolling along their associate patrol path. | Partial pass | Only a single guard / patrol path is working as intended. Additional guards / paths cause their guards to walk to the center of the path, and then stop moving. | LogScript: Warning: Script Msg: Attempted to access index 0 from array 'PatrolWaypoints' of length 0 in '/Game/NPC/Pathing/BP_PatrolComponent.BP_PatrolComponent_C'! LogScript: Warning: Script Msg called by: BP_PatrolComponent_C /Game/Levels/UEDPIE_0_MuseumLevel.MuseumLevel:PersistentLevel.BP_BaseEnemy_C_1.BP_PatrolComponent PIE: Error: Blueprint Runtime Error: "Accessed None trying to read property CallFunc_Array_Get_Item". Node: Return Node Graph: GetCurrentWaypointLocation Function: Get Current Waypoint Location Blueprint: BP_PatrolComponent | Implement a condition to tie specific guard / enemy instances to additional patrol path instances.
Security camera catches player when they are within the overlap / trigger area for the camera | When a player is detected as having crossed into the trigger area of a security camera’s vision / catch event, the player should be caught, triggering a mission failure. | Fail | The catch / mission failure mechanic is not currently implemented so security camera cannot catch the player. The implementation I have can do damage, but I need change the behavior to use a timer to alternate movement instead of snapping to the player when they enter range. | N/A. No runtime error occurs | Implement a mission failure mechanic to be triggered by events that cause the player to fail the mission. Set this event to trigger when a player enters the region of a security camera’s vision / trigger event. The camera must also be implemented. Base BP that will be use for camera is added, but projectile / detection beam needs to be adjusted. Detection beam overlap with player will trigger death / respawn / mission failure.
Laser security beam trap will trigger when a player passes through the trigger range that is associated with the laser’s beam. | When a player crosses too close (passes through or makes contact) to the laser beam, alarms are sounded and the player is caught. | Fail | The catch mechanic is not yet implemented, the laser beam and associated trigger / detection radius must also be implemented first | N/A. No runtime error occurs | This will be fixed by implementing a tight trigger radius within the beam of the laser. The laser beam must be implemented, and the begin trigger range should trigger the catch mechanism once it is also implemented.