## Traceability Matrix
Traceability Matrix
Prototype Title: | Purr-loin
Scope: | This game is a third-person stealth / sneaking game. The player must use their skills as a cat-burglar to sneak past guard dogs and gather valuables as they work to complete their mission. The player will have a primary objective (level-based), a secondary objective (to escape), and a bonus objective (to gather additional valuables from the level).
Bitbucket Repository Link: | https://bitbucket.org/johnson-arena-c3-2024/johnson_arena/src/main/
Class | Functionality | Implementation Description | Program | Begin Phase | Complete Phase | Assigned to | Completed? Y/N | Notes
Example: Player Character | Example: Movement | Example: Utilize WASD input keys to control player speed and direction. | Example: Unreal Engine 5 | Example: Pre-alpha | Example: Alpha | Example: Self | Example: Yes | Example: Movement is completed, but inputs need to be added to project settings.
Player Character | Movement | Utilize WASD input keys to control player speed and direction. | Unreal Engine 5.4.0, Git, | Pre-alpha | Pre-alpha | E. Johnson, | No | Base movement is implemented (WASD), additional inputs may be needed
Player Character | Pick-up Items | Utilize E input key to interact / pick up objects. | Unreal Engine 5.4.0, Git, | Pre-alpha | Pre-alpha | E. Johnson, | No | Input is implemented and items can be interacted with / taken. No system is currently implemented to handle storage / tracking of picked up items.
Player Character | Item scoring | Implement the scoring for bonus item pickups | Unreal Engine 5.4.0, Git, | Pre-alpha | Pre-alpha | E. Johnson, | No | No system has been implemented yet.
Player Character | Hide interaction | Utilize tab input key to hide the player behind an object / terrain. | Unreal Engine 5.4.0, Git, | Pre-alpha | Alpha | E. Johnson, | No | Hide input and object interaction has not yet been implemented.
Player Character | Model | Base model selection and implementation for the player character | Unreal Engine 5.4.0, Git, | Alpha | Alpha | E. Johnson, | No | Not yet implemented, will be in Alpha +
Player Character | Animations | Implement animations for the player model for the various interactions | Unreal Engine 5.4.0, Git, | Alpha | Alpha | E. Johnson, | No | Not yet implemented, will be in Alpha +
Player Character | Movement | Utilize the space bar to allow the player to jump over obstacles or traps such as laser detector beams | Unreal Engine 5.4.0, Git, | Pre-alpha | Pre-alpha | E. Johnson, | No | Jump movement is implemented and working. When the player presses space bar, their character will move vertically.
Player Character | Trap interaction | The player will press F to interact with a trap, attempting to use their disarming skills (claw) to pick / disable the trap | Unreal Engine 5.4.0, Git, | Pre-alpha | Alpha | E. Johnson, | No | The input key will need to be created, as well as the animation for this ability, and each corresponding trap will need the interaction area/range for this ability to be defined
Security Guard Dog: NPC | Movement | Implement patrol paths for controlling the range of a guard | Unreal Engine 5.4.0, Git, | Pre-alpha | Alpha | E. Johnson, | No | Not yet implemented
Security Guard Dog: NPC | Vision | Implement visual cues to show the distance that a guard can see the player from (i.e. flashlight beam) | Unreal Engine 5.4.0, Git, | Pre-alpha | Alpha | E. Johnson, | No | Not yet implemented
Security Guard Dog: NPC | Interactions | Implement the interaction with a player (Catching a player) | Unreal Engine 5.4.0, Git, | Pre-alpha |  | E. Johnson, | No | System for catching a player / failing the level not yet implemented
Security Guard Dog: NPC | Model | Implement the model selection for the guard dog NPC | Unreal Engine 5.4.0, Git, | Pre-alpha | Alpha | E. Johnson, | No | Not yet implemented, will be in Alpha +
Security Guard Dog: NPC | Animations | Model animations for the guard dog | Unreal Engine 5.4.0, Git, | Pre-alpha | Alpha | E. Johnson, | No | Not yet implemented, will be in Alpha +
Security Camera: Game Obstacle / Trap | Object | Implement the object / class for security camera | Unreal Engine 5.4.0, Git, | Pre-alpha | Pre-alpha | E. Johnson, | No | Not yet implemented
Security Camera: Game Obstacle / Trap | Vision | Implement visual cues to show the distance that a security camera can see the player from (i.e. tracking laser paired with overlap trigger area) | Unreal Engine 5.4.0, Git, | Pre-alpha | Pre-alpha | E. Johnson, | No | Not yet implemented
Security Camera: Game Obstacle / Trap | Animations | Implement animations security camera | Unreal Engine 5.4.0, Git, | Alpha | Alpha | E. Johnson, | No | Not yet implemented, will be in Alpha +
Laser Beam Trip-wire: Game Obstacle / Trap | Object | Implement a laser beam trip fire that features a very tight overlap trigger that will cause alarms to be set off and the player to be found if they do not maneuver around it. | Unreal Engine 5.4.0, Git, | Pre-alpha | Alpha | E. Johnson, | No | Not yet implemented. Should be added along with guard dogs, and security cameras as the primary obstacles players to face.
Laser Beam Trip-wire: Game Obstacle / Trap | Animations | Implement animations / variations for any laser trip wires that have movement / alternative patterns. | Unreal Engine 5.4.0, Git, | Pre-alpha | Alpha | E. Johnson, | No | Not yet implemented. Should be added along with guard dogs, and security cameras as the primary obstacles for players to face.
Game mechanic | Level timer | Implement a timer for the level. The player will fail the level if the timer runs out before they have completed the main objective and reached the exit / escape point | Unreal Engine 5.4.0, Git, | Pre-alpha | Alpha | E. Johnson, | No | Core game feature, not yet implemented. High priority
Game mechanic | Level failure | Implement the level failure mechanic that will be called whenever the player character triggers a trap or is caught by one of the other obstacles they may face | Unreal Engine 5.4.0, Git, | Pre-alpha | Pre-alpha | E. Johnson, | No | Not yet implemented. Should be added before the guard dogs, and security cameras as this will be a core game mechanic needed in the implementation of other game features.
User interface | Graphical User Interface | Implement GUI valuable score tracker for player U.I. | Unreal Engine 5.4.0, Git, | Pre-alpha | Alpha | E. Johnson, | No | Not yet implemented, will be in Alpha once core game mechanics are added.
User interface | Graphical User Interface | Implement GUI main objective tracker for player U.I. | Unreal Engine 5.4.0, Git, | Pre-alpha | Alpha | E. Johnson, | No | Not yet implemented, will be in Alpha once core game mechanics are added.
User interface | Graphical User Interface | Implement GUI secondary objective tracker for player U.I. | Unreal Engine 5.4.0, Git, | Pre-alpha | Alpha | E. Johnson, | No | Not yet implemented, will be in Alpha once core game mechanics are added.
User interface | GUI – is player hidden? | Implement player U.I. visibility / status tracker | Unreal Engine 5.4.0, Git, | Pre-alpha | Alpha | E. Johnson, | No | Not yet implemented, will be in Alpha once core game mechanics are added.

## Test Plan
Test Plan
Bitbucket Repository Link: | https://bitbucket.org/johnson-arena-c3-2024/johnson_arena/src/main/
Test Feature | Description of Test | Pass/Fail | Bugs | Runtime Errors | Updates/Error Resolution
Example: Pickup interaction | Example: Implement print strings to ensure player input is firing and appropriate events are being called. Display class name on interaction via print string to ensure the correct class is interacting. | Example: Fail | Example: Pickup interaction functions, but integer doesn't increment properly. | Example: Accessed None when trying to read Pickup_BP | Example: Verify item interaction is setting the Pickup_BP references variable properly. An issue here may be why the variable cannot be accessed by the editor.
Item / objective pickup interaction | When an object is picked up by the player, bonus objective or primary objective should be updated respectively | Fail | Pickup interaction works correctly, but there is no tracking or object class / type system implemented to update objective when item is acquired | N/A. No runtime error occurs | Implement item classes to update appropriate objectives when an item is acquired
Player score increment on item pickup | When a player picks up an object that is tied to the bonus objective class, the bonus score should be appropriately incremented to reflect the pickup | Fail | Pickup interaction works correctly, but bonus score is not incremented | N/A. No runtime error occurs | Implement an addition to the score value to occur when an item that is designated as a bonus objective class is picked up
Player hiding won’t be detected | When a player has successfully triggered the hide ability, they should be hidden from any patrolling guard dogs. | Fail | Hide input is not mapped, the interaction is not currently implemented, hiding is not currently possible | N/A. No runtime error occurs | Implement a player character input to trigger hide. Implement boolean state variable to check whether the player is currently hidden
Guard dog catches player in line of sight / within overlap trigger area | When a player is detected as having crossed into the trigger area of a guard dog’s catch event, the player should be caught, triggering a mission failure. | Fail | The catch / mission failure mechanic is not currently implemented so a guard dog cannot catch the player. The | N/A. No runtime error occurs | Implement a mission failure mechanic to be triggered by events that cause the player to fail the mission. Set this event to trigger when a player enters the region of a guard dog’s vision / trigger event. Need to implement the patrolling guard dog along with a realistic trigger event radius.
Security camera catches player when they are within the overlap / trigger area for the camera | When a player is detected as having crossed into the trigger area of a security camera’s vision / catch event, the player should be caught, triggering a mission failure. | Fail | The catch / mission failure mechanic is not currently implemented so security camera cannot catch the player. | N/A. No runtime error occurs | Implement a mission failure mechanic to be triggered by events that cause the player to fail the mission. Set this event to trigger when a player enters the region of a security camera’s vision / trigger event. The camera must also be implemented
Laser security beam trap will trigger when a player passes through the trigger range that is associated with the laser’s beam. | When a player crosses too close (passes through or makes contact) to the laser beam, alarms are sounded and the player is caught. | Fail | The catch mechanic is not yet implemented, the laser beam and associated trigger / detection radius must also be implemented first | N/A. No runtime error occurs | This will be fixed by implementing a tight trigger radius within the beam of the laser. The laser beam must be implemented, and the begin trigger range should trigger the catch mechanism once it is also implemented.